## Slide 1: Mandela Washington Fellowship
INTERNATIONAL PROGRAM MANAGEMENT
Bobby Dodd Institute in partnership with IREX
Agnes Iwaye
Program Manager
3
cycles
5
Fellows
Notes: Portfolio case study based on Agnes Iwaye’s first-person account. BDI = Bobby Dodd Institute. Cycle years, actual costs and Fellow nationalities were not supplied.

## Slide 2: Program context and BDI’s scope
The wider Fellowship
A U.S. Department of State program funded by the U.S. Government and administered by IREX.
49
countries in the wider Sub-Saharan Africa network
My host-organization role
Managed BDI’s participation across three cycles, supporting five Fellows through selection, arrival, professional placement and departure.
3
cycles
5
Fellows
49 countries describes the program network. BDI Fellows’ countries were not supplied.
Notes: Sources: https://www.mandelawashingtonfellowship.org/ and https://www.mandelawashingtonfellowship.org/about/ (accessed October 5, 2026). BDI scope: Agnes Iwaye’s supplied account. Program-wide figures do not describe the nationalities of BDI’s five Fellows.

## Slide 3: The hosting challenge
Program objective
Create meaningful professional placements that connect Fellows’ interests with BDI’s mission and program teams.
Coordination requirements
Align selection decisions with IREX.
Prepare Fellows for arrival and orientation.
Coordinate activities with BDI program managers and support return travel.
Notes: Source: Agnes Iwaye’s supplied account of her BDI Fellowship role.

## Slide 4: My responsibilities across the lifecycle
Selection
Worked with IREX to review and select Fellows for BDI.
Pre-arrival
Supported travel readiness and arrival coordination.
Onboarding
Introduced Fellows to BDI and the program’s intent.
Placement
Connected Fellows with BDI program managers and activities.
Departure
Supported return travel and the transition out of the placement.
Notes: Source: Agnes Iwaye’s supplied account of her BDI Fellowship role.

## Slide 5: Participation across three cycles
Chart: Fellows supported per cycle
| Cycle 1 | Cycle 2 | Cycle 3
Fellows supported | 1 | 1 | 3
20%
Cycle 1 share
20%
Cycle 2 share
60%
Cycle 3 share
3×
The third cycle hosted three times as many Fellows as either earlier cycle.
Notes: Source: Agnes Iwaye’s supplied account of her BDI Fellowship role.

## Slide 6: Stakeholder coordination
IREX
Fellow selection, placement requirements and program coordination
Agnes Iwaye, BDI
Host coordination, onboarding, logistics and participant support
BDI program managers
Workplace activities and professional placement support
Fellows
Travel readiness, learning interests and participation
My role connected the external program administrator with BDI’s internal delivery teams.
Notes: Source: Agnes Iwaye’s supplied account of her BDI Fellowship role.

## Slide 7: Illustrative timeline for one hosting cycle
Weeks 1–2
Review Fellow profiles and confirm placement alignment with IREX.
Weeks 3–4
Prepare travel, schedules and internal host arrangements.
Week 5
Welcome Fellows and complete BDI orientation.
Weeks 5–8
Deliver a modeled four-week professional placement.
Week 9
Support departure and capture feedback.
Illustrative only. The 2025 PDE lasted four weeks. The general program overview allows up to six. BDI’s actual cycle dates remain unconfirmed.
Notes: Illustrative planning model, not historical BDI dates. Sources: https://www.mandelawashingtonfellowship.org/about/ and https://www.mandelawashingtonfellowship.org/2025/06/23/2025-mandela-washington-fellows-arrive-in-the-united-states/ . The general overview allows PDEs up to six weeks. The 2025 announcement specifies four weeks. Leadership Institutes are a separate six-week component.

## Slide 8: Suggested controls for future cycles
Arrival or departure disruption
Confirm itineraries and escalation contacts with IREX.
Placement mismatch
Agree learning objectives and a named BDI supervisor.
Schedule conflicts
Maintain one shared calendar and review it weekly.
Participant support needs
Schedule regular check-ins and clarify the support contact.
Incomplete closeout
Use a departure checklist and request participant feedback.
RISK
SUGGESTED CONTROL
Notes: Suggested operating controls for a future hosting cycle. These are portfolio planning examples, not assertions that Agnes used these exact documents or practices historically.

## Slide 9: Reported outcomes and skills demonstrated
Reported outcomes
Managed three hosting cycles.
Supported five Fellows, with three in the final cycle.
One participating Fellow later secured external funding.
Skills demonstrated
International program management
IREX and stakeholder coordination
Participant selection and onboarding
Travel and placement coordination
Funding outcome: Agnes identified the funder as “Afro Black Foundation.” Award details were not supplied, and a causal link to BDI is not established.
Notes: Source: Agnes Iwaye’s supplied account of her BDI Fellowship role.

## Slide 10: Sources and evidence notes
Project evidence
Agnes Iwaye’s account: BDI program manager, IREX selection partnership, three cycles with 1, 1 and 3 Fellows, travel support, orientation, placement coordination and one later funding outcome.
Official program sources
mandelawashingtonfellowship.org/
mandelawashingtonfellowship.org/about/
mandelawashingtonfellowship.org/pde/
2025 Fellows arrival announcement, June 23, 2025
Timeline, budget and suggested controls are illustrative. Cycle years and actual costs remain unconfirmed.
Notes: Sources accessed October 5, 2026: https://www.mandelawashingtonfellowship.org/ ; https://www.mandelawashingtonfellowship.org/about/ ; https://www.mandelawashingtonfellowship.org/pde/ ; https://www.mandelawashingtonfellowship.org/2025/06/23/2025-mandela-washington-fellows-arrive-in-the-united-states/ . All project-specific evidence comes from Agnes Iwaye’s supplied narrative.